## Budget and Treasury
Moses Kotane Local Municipality 3rd Quarter Performance Report 2020-2021 financial year
Key Performance Indicators | Annual Target 2020/21 | 2018/2019 Baseline | Quarterly | 3rd Quarter Actual Performance | 3rd Quarter Actual Performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence(POE)
 KPA 6: Municipal Financial Viability  provide an anti-fraud corruption strategy  to provide an effective and efficient financial systems and procedures
KPI 70 2021/2022 Draft budget approved by Council | 2021/2022 Draft budget approved by Council by 31 March 2021 | 2020/2021 Draft Budget approved | Q3 | Approved Draft budget | Draft budget approved | Operational | Operational | none | none | Council Resolution
KPI 71 2021/2022 Final budget approved by Council | 2021/2022 Final budget approved by Council by 31 May 2021 | 2020/2021 Final Budget approved | Q3 | - |  | Operational | Operational | N/A | N/A | N/A
KPI 72 2019/2020 Annual Financial statements submitted to Auditor General | 2019/2020 Annual Financial statements submitted to Auditor General by 31 August 2020 | 2018/2019 Financial statements submitted | Q3 |  | N/A | Operational | Operational | none | none | N/A
KPI 73 Number of MFMA Section 52 Reports approved Council | 4 MFMA Section 52 Reports approved by Council by 30 June 2021 | 2019/2020 MFMA Section 52 reports | Q3 | 1 MFMA Section 52 Report | 1 MFMA Section 52 report compiled | Operational | Operational | none | none | Council Resolution
KPI 74 Percentage of competitive bids awarded within 90 days of advert | 100% of competitive bids awarded within 90 days of advert by 30 June 2021 | 100% of competitive bids awarded within 90 days of advert by June 2020 | Q3 | 100% advertised bids awarded within 90 days of advert |  | Operational | Operational | tenders closed towards the end of the quarter, making it impractial to consider and finalise before end of the quarter . Some tenders closing date overlapped to the 4th quarter | adhere to the dates sets on the procurement plan and effective siitting of bid committees | Adverts and appointment letters
KPI 75 Percentage of request for quotations awarded within 30 days of advert | 100% of request for quotations awarded within 30 days of advert by 30 June 2021 | 100% of RFQ quotations awarded within 30 days of advert by June 2020 | Q3 | 100% of RFQ quotations awarded within 30 days of advert | 100% | Operational | Operational | none | none | Adverts and purchase orders
KPI 76 % of indigent register updated | 100 % of indigent register updated by 30 June 2021 | new | Q3 | 100 % of indigent register updated | 32% | Operational | Operational | None renewal of indigent applications and collection of FBE 50kwh of electricity at Eskom | Ward committees are currently busy with assisting In new registration of indigent | Updated indigent register
KPI 77 % revenue growth | 10% revenue growth by 30 June 2021 | 2019/2020 Revenue collected | Q3 | 2,5 % revenue growth | 49% | Operational | 2353039 | none | none | 90-day age analysis report
KPI 78 % of asset register updated | % 100 of asset register updated by 30 June 2021 | 1 report on Immovable and movable Asset Verification by June 2020 | Q3 | 100 % asset register updated | 100% asset register updated | Operational | Operational | none | none | Stock count Report

## Corporate Service
Moses Kotane Local Municipality 3rd Quarter Performance Report 2020-2021 financial year
Key Performance indicator | 2020/2021 Annual Targets | 2019-2020 Baseline | Quarter | 2020/2021 Quarterly Targets | 3rd quarter actual performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence
KPA 1: Municipal Transformation and Organizational Development
Strategic Objective: To Promote Accountability, Efficiency and Professionalism Within the Organization
KPI 24 Communication strategy reviewed by council | Communication strategy reviewed by council by June 2021 | 2019-2020 Communication strategy | Q3 | 1 reviewed strategy | Not achieved. Strategy reviewed but await approval by council | Operational | Operational | Portfolio meetings not taking place | the strategy will be submitted in the fourth quarter | None
KPI 25 Number of Newsletters Published per quarter | 4 newsletters published by June 2021 | 3 newsletters | Q3 | 1 newsletter per quarter | Achieved. 1 report newsletter published | Operational | Operational | none | none | Copy of the Newsletter attached
KPI 26 Employment Equity Report submitted to Department of Labour | 1 report submitted to the Department of Labor by 15 January 2021 | 2019-2020 Employment Equity Report | Q3 | EE report submitted to DOL | Not Achieved | Operational | Operational | Employment Equity Plan not developed | Plan to be developed in the fourth quarter | none
KPI 27 Work Skills Plan submitted to LG_SETA | WSP submitted LG­ ­SETA by April 2021 | 2019-2020 WSP submitted | Q3 | _ | N/A | Operational | Operational | n/a | n/a | n/a
KPI 28 Number of Local Labour Forum meetings held | 4 LLF meetings held by June 2021 | 2 LLF meetings | Q3 | 1 meetings | Not Achieved. No meeting held | Operational | Operational | none | none | None
KPI 29 Percentage of grievances resolved within 30 days | 100% of grievances resolved within 30 days by June 2021 | New | Q3 | 100% | No new grievances recorded | Operational | Operational | none | none | none
KPI 30 Organisational Structure approved by council | Organizational structure approved by council by March 2021 | Reviewed organisational | Q3 | approved organizational structure | Achieved in 1st quarter | Operational | Operational | none | none | Council resolution
KPI 31 Number of the OHS meetings held | 4 OHS meetings held by June 2021 | 4 OHS meetings | Q3 | 1 meeting | Not Achieved | Operational | Operational | The meeting was postponed due to poor attedance | intervention will be done for office of the HOD: Corporate services | none
KPI 32 Percentage of fleet management budget spent | 100% of fleet management budget spent by June 2021 | New | Q3 | 25%of fleet management budget spent | Achieved. 36.6 % | Operational | R 1829 917.36 |  |  | Quarterly expenditure reports
KPI 33 Percentage of ICT budget spent by June 2021 | 100% of ICT budget spent by June 2021 | 100% budget spent | Q3 | 25% | 24.7% spent | Operational | R 1948, 85 | late submission and payment of invoices | fast track timeous submission of invoices. | Quarterly expenditure reports
KPA5 : Good Governance and Public Participation  Strategic Objectives: To be an ethical and transparent local government that is responsive to the needs of the community and encourage public participation  To strengthen intergovernmental relations IGR and stakeholder relation  To improve the standard of the Intergraded Development Plan  To Manage Performance Management System  To manage organizational risk
KPI 38 Number of Mayoral Imbizo held by June 2021 | 1 mayoral Imbizo by June 2021 | New | Q3 | _ | not yet due | 340000 |  | none | none | Attendance registers, Imbizo report
KPI 39 Number of Letsema programmes conducted | 2 letsema programme conducted by 30 June 2021 | New | Q3 | 2 letsema programme conducted | Not achieved. No programme was implemented | 100000 |  | Letsema programmes not implemented due to Lockdown Regulations | Programmes to be done in the next financial year | Attendance registers and minutes
KPI 40 Number of physically/diasbled challenged meetings held | physically/diasbled challenged meetings held by 30 June 2021 | New | Q3 | 1 physically/diasbled challenged meetings held | Not achieved. No meeting was held | 200000 |  | Meetings could not be arranged due to lockdown regulations | Meetings will take place in the next financial year | Attendance registers and minutes
KPI 41 Number of functional Council committee meetings held | 6 functional council committee meetings by June 2021 | 4 functional council committee meetings | Q3 | 1 functional council committees | 3 Council Meetings held | Operational |  | none | none | Agenda, Attendance register and minutes
KPI 42 Numbers of EXCO meeting held | 12 EXCO Meetings held by June 2021. | 12 meeting | Q3 | 3 meetings | 3 EXCO Meetings held | Operational | Operational | none | none | Agenda, attendance register and minutes

## Community Services
Moses Kotane Local Municipality 3rd Quarter Performance Report 2020-2021 financial yea
Key Performance Indicators | 2020/2021 Annual Target | 2019/2020 Baseline | Quarter | Quarterly Targets | Quarter Actual | Status( Achieved/Not Achieved | Budget | Expenditure | Challenges/ Reasons for Underperformance | Measures taken to improve performance | POE
KPA 1 : Basic Service Delivery and Infrastructure Development  Strategic objective: Development and maintenance of infrastructure to provide basic services  To develop and improve community infrastructure facilities, public safety, disaster emergencies and healthy environment
KPI 14 Contingency Disaster Management Plan approved by Council | Contingency Disaster Management Plan approved by Council by June 2021 | New | Q3 | N/A | N/A | N/A | Operational | None | N/a | N/A | none
KPI 15 Crime Prevention Plan approved by Council | Crime Prevention Plan approved by Council by June 2021 | New | Q3 | N/A | N/A | N/A | 200000 | None | N/a | N/a | none
KPI 16Number of Road Safety awareness campaign conducted per quarter | 12 road safety awareness campaigns conducted by June 2021 | 12 road safety awareness campaigns | Q3 | 3 Road safety campaigns were conducted |  | Achieved | 200000 | None | None | None | Attendance Register and Report
KPI 17% upgrade of Madikwe Landfill site(ward 19) | 60% upgrade of Madikwe Landfill site by June 20221 | Rehabilitation of Madikwe Landfill Site | Q3 | N/A | Resubmission and rectification in progress | Not Achieved | 3000000 | None | None | None | Progress Report
KPI 18 % of households which have access to solid waste removal | 100% of households which have access to solid waste removal by June 2021 | Solid waste removal | Q3 | N/A | 100% of households received solid waste removal services | Achieved | 18800000 | None | None | None | Solid Waste Removal Report
KPI 19Number of safe and clean-up campaigns conducted | 12 safe and clean-up campaigns conducted by June 2021 | 12 campaigns | Q3 | 3 safe and clean-up Municipality campaigns conducted | Madikwe on the 12th March 2021, Mogwase 26th February 2021 and Moruleng 31 March 2021 | Achieved | 100000 | None | None | None | Attendance Register and Report
KPI 20Number of Land fill site external environmental audits conducted in Mogwase and Madikwe | 2 Landfill site external environmental audits conducted in Madikwe and Mogwase by June 2021 | 8 | Q3 | N/A | None |  | 65124.96 | None |  |  | Environmental Audit Reportt
KPI 21 Mogwase Sport park upgraded | Mogwase Sports park udgraded by June 2021 | New | Q3 |  | The Project is on construction stage. |  | 9864475 | None |  |  | Completion Certificate
KPI 22 Number of Municipal Buildings Repaired | 4 Municipal buildings repaired/renovated by June 2021 | 6 | Q3 | 1 municipal building repaired/renovated | 1 Municipal buildings repaired,Pella Water plant staff houses renovated | Achieved | 4000000 | 970000 | None | None | Completion Certificate
KPI 23 Approved Library business pla submitted to Department of Arts and Culture | Library business plan approved submitted to Department of Arts and Culture by June 2021 | Library business plan | Q3 | Expenditure continnues | N/A | Achieved | Operational |  | None | None | Business plan approved

## Planning and Developement
Moses Kotane Local Municipality Third Quarter Performance Report 2020-2021 financial year
Key Performance indicator | 2020/2021 Annual Targets | 2019-2020 Baseline | Quarter | 2020/2021 Quarterly Targets | 3rd Quarter Actual Performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence
KPA4: Spatial Rationale  To establish economically, socially and environmentally integrated sustainable land use and human settlement in MKLM. Department Planning and Development
KPI 66 Mogwase Unit 6 Township establishment approved | Mogwase Unit 6 Township establishment by June 2021 | New | Q1 |  |  | Human Settlement Development Grant (HSDG) | n/a | n/a | n/a | Approval letter
KPI 67 Mogwase Unit 7 Township establishment approved | Approval of Mogwase Unit 7 Township establishment by June 2021 | New | Q1 | Consideration of the application |  | Human Settlement Development Grant (HSDG) | n/a | n/a | n/a | Approval letter
KPI 68 % of Building inspections attended to within 24 hours of request | % of building inspections attended to within 24 working hours of request by June 2021 | New | Q1 | 100% housing inspections attended to within 24 hours of request | 100% housing inspections were attended | Operational | operational | none | none | Inspection register
KPI 69 % of Building plans approved within 4 weeks of request | 100% of Building plans approved within 4 weeks of request by June 2021 | New | Q1 | 100% Building Plans approved within 4 weeks of request | No building plans were submitted or approved within 4 weeks | Operational | operational | none | none | Building Plans Register

## Local Economic Development
Moses Kotane Local Municipality Third Quarter Performance Report 2020-2021 financial year
Key Performance indicator | 2020/2021 Annual Targets | 2019-2020 Baseline | Quarter | 2020/2021 Quarterly Targets | 3rd Quarter Actual Performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence
KPA: Local Economic Development
Strategic Objective: To create an enabling environment for social development and economic growth
KPI 60 LED strategy approved by council | LED strategy approved by council by June 2021 | 2011 LED strategy | Q3 | N/A | N/A | 3000000 | N/A | N/A | N/A | N/A
KPI 61 Arts and Culture Masterplan approved by council | Arts and Culture Masterplan approved by council by end June 2021 | Provincial & National policy guideline | Q1 | N/A | N/A | 3000000 | N/A | N/A | N/A | N/A
KPI 62 Number of job opportunities created through EPWP and capital projects | 340 Job opportunities created through EPWP and capital projects by June 2021 | 187 Job opportunities created | Q3 | 100 Jobs | ACHIEVED EPWP=110 Capital Proj=49 | 1827000 | R1400 949.00 | none | none | Beneficiaries’ list and contracts/ EPWP system reports
KPI 63 Number jobs created through municipality’s local economic development initiatives | 200 jobs created through municipality’s local economic development initiatives by June 2021 | 200 jobs | Q3 | 47 jobs created through municipality’s local economic development initiatives | ACHIEVED Tourism =5 Grass Cutting & Cleaning of roads =132 | Operational | operational | none | none | Beneficiaries list and comprehensive report
KPI 64 Feasibility study for establishment of fresh produced market (Vegetable Market) conducted | Feasibility study for establishment of fresh produced market (Vegetable Market) conducted by June 2021 | New | Q3 | - | N/A | R7,223 512 | N/A | N/A | N/A | N/A
KPI 65 Number of LED projects financially supported | 6 LED projects financially supported by June 2021 | 04 projects | Q3 | - | N/A | R7,223 512 | N/A | N/A | N/A | N/A

## Infrastrucrure and Technical
Moses Kotane Local Municipality Third Quarter Performance Report 2020-2021 financial year
Key Performance indicator | 2020/2021 Annual Targets | 2019-2020 Baseline | Quarter | 2020/2021 Quarterly Targets | 3rd Quarter Actual Performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence
KPA 1 : Basic Service Delivery and Infrastructure Development  Strategic objective: Development and maintenance of infrastructure to provide basic services  To develop and improve community infrastructure facilities, public safety, disaster emergencies and healthy environment
KPI 1 Madikwe Water Treatment works upgraded | Madikwe Water Treatment works upgraded by 30 June 2021 | Existing works | Q3 | project to be completed in the 4th quarter | 32% complete | R6 000 000 | 2345608.92 | None | N/A | Progress reports
KPI 2 Number of water supply schemes Constructed | 6 water supply schemes Constructed by June 2021 (Letlhakane / Kortkloof, Pitsedisulejang, Letsheng, Makoshong, Tweelagte & Lossmytjerrie/Goedehoop) | Existing works | Q3 | project to be completed in the 4th quarter | 55% completed | R 55 000 000 | 12202120.6234 | None | N/A | Progress reports
KPI 3 % of water supply schemes constructed | 40% constructed by June 2021 (Sandfontein, Maolone, Ledig) | Ledig: Phase 1 | Q3 | project to be completed in the 4th quarter |  | R17 369 441 | 1381000 | Awaiting DWS reccomendation letters | N/A | Progress reports
KPI 4 Madikwe Water safety plan approved by council | Madikwe Water safety plan approved by council by June 2021 | new | Q3 | project to be completed in the 4th quarter | Draft water safety plan | 100000 |  | information required from other deprtments, due covid 19 regulation. Personnel coming to work on schedules. | improve communication and coordination with other departments, also to seek how best can we share information | council resolution
KPI 5 The percentage of households with access to basic level of water | 100% of households with access to basic level of water | 100% of households with access to basic level of water | Q3 | 100% | 99.7% | 75000 | N/A | N/A | N/A | Applications & Completed site records
KPI 6 Number of VIP toilets constructed | 1618 VIP toilets constructed by June 2021 | 605 | Q3 | project to be completed in the 4th quarter | 65% completed | R 25 887 357 | 22090163.37 | community protests and heavy rains leading to project stoppage | N/A | Progress Reports
KPI 7 Road Master Plan approved By Council | Road Master Plan approved by Council by June 2021 | Draft master plan | Q3 | project to be completed in the 4th quarter |  | Operational |  | N/A | N/A | council resolution
KPI 8 Number of km of internal roads constructed | 9 km of internal road constructed by June 2021 (3km per village. Ramoga, Madikwe & Tlokweng) | 12 km paved internal roads | Q3 | project to be completed in the 4th quarter | 51% completed | R 42 425 000 | 17601273.51 | Heavy rains leading to project stoppages | N/A | Progress reports
KPI 9 Number of km of internal roads constructed | 9,8km of paved internal roads constructed by 30 June 2020 (Mabodisa, Mmorogong , Leruleng) | new | Q3 | project to be completed in the 4th quarter | 100% completed | 10726783 | R10 726 783 | None | N/A | Completion certificates
KPI 10 Greater Moruleng storm water management constructed | Greater Moruleng storm water management constructed by June 2021 | new | Q3 | project to be completed in the 4th quarter | Design Completed | 6100000 | 5929499 | None | N/A | Technical Report
KPI 11 Vrede storm-water designs approved by DEDECT | Vrede Storm-water design approved by DEDECT by June 2021 | 12 km paved internal roads | Q3 | project to be completed in the 4th quarter | Feasibility report | R 2 000 000 | 1567374 | Awaiting approval letter by DEDECT | All requested documents have been sent to DWS for reccommendation | Approval Letter by DEDECT
KPI 12 Number of high-mast lights installed | 28 of high-mast lights installed by June 2021 (5 Mmopyane, 4 Ramotlhajwe, 4 David Katnagel, 5 Pitsedisulejang, 3 Ramokgolela 2 Ramokokas 5 Letlhakeng) | New | Q3 | project to be completed in the 4th quarter | 54% completed | R9 326 981.00 | N/A | N/A | N/A | Progress reports
KPI 13 Number of high mast lights installed | 22 high mast lights energised 30 June 2021 | 25 High mast lights | Q3 | project to be completed in the 4th quarter | 7 light paid for eskom to energise | 3184796 | 401876.17 | Slow response of Eskom to energise masts and other infrastructure | High level intervention required to intevine in the matter | Proof of payment

## MM's Office
Moses Kotane Local Municipality Third Quarter Performance Report 2020-2021 financial year
Key Performance indicator | 2020/2021 Annual Targets | 2019-2020 Baseline | Quarter | 2020/2021 Quarterly Targets | 3rd Quarter Actual Performance | Annual Budget | YTD Expenditure | Challenges | Corrective Measures | Portfolio of Evidence
KPA 1: Municipal Transformation and Organizational Development
Strategic Objective: To Promote Accountability, Efficiency and Professionalism Within the Organization
KPI 34 2021/2022 institutional performance management framework approved by Council | 2021/2022 institutional performance management framework approved by Council by June 2021 | 2020/2021 Performance Management framework approved | Q3 | N/A | N/A | Operational | N/A | N/A | N/A | Council Resolution
KPI 35 2019/2020 annual performance report submitted to Auditor General | 2019-2020 annual performance report submitted to Auditor General by August 2020 | 2018/2019 annual performance report | Q3 | N/A | N/A | Operational | N/A | N/A | N/A | Council Resolution
KPI 36 2019/2020 Annual report approved by Council | 2019/2020 annual report approved by council by January 2021 | 2017/2018 Annual Report | Q3 | Approved 2018/2019 annual report | Approved 2018/2019 annual report | Operational | N/A | N/A | N/A | Council Resolution
KPI 37 Number of 2020/2021 performance agreements signed by Municipal Manager and Section 56 managers | 7 2020/2021 performance agreements signed by Municipal Manager and Section 56 managers by July 2010 | 6 signed 2019/2020 Performance Agreements | Q3 | N/A | N/A | Operational | N/A | N/A | N/A | Copies of signed Performance Agreements
KPA5 Good Governance and Public Participation  Strategic Objectives: To be an ethical and transparent local government that is responsive to the needs of the community and encourage public participation  To strengthen intergovernmental relations IGR and stakeholder relation  To improve the standard of the Intergraded Development Plan  To Manage Performance Management System  To manage organizational risk
Review 2020-2021 internal audit charter for audit committee approval | Audit committee approved 2020/2021 internal audit charter by 30 September 2020 | 2019/2020 Internal audit charter | Q3 | 2020/2021 Internal audit charter | N/A | Operational | N/A | N/A | N/A | N/A
Revise 2020-2021 Risk Based Audit Plan (RBAP) for audit committee approval | Audit committee approved 2020-2021 Risk Based Audit Plan (RBAP) by 30 September 2020 | 2019/2020 Approved Risk Based Audit Plan (RBAP) | Q3 | 2020/2021 Internal audit methodology | N/A | Operational | N/A | N/A | N/A | N/A
Number of audit committee meetings held | 4 audit committee meetings held by June 2021 | 4 audit committee meetings | Q3 | 1 audit committee meeting held | 1 audit committee meeting held | Operational | Operational | N/A | N/A | Agenda, minutes and attendance register.
Number of audit committee reports submitted to Council | 2 audit committee reports submitted to Council by 30 June 2021 | 2 audit committee reports | Q3 | audit committee reports | audit committee reports compiled | Operational |  | N/A | N/A | Council Resolution
2020/2021 valuation roll approved by Council | 2020/2021 valuation roll approved by Council by | Approved valuation roll for 2018/2019 | Q3 | Approved valuation roll | Approved valuation roll | Operational |  | N/A | N/A | Council Resolution
Turnaround time for providing legal opinion on by-laws upon request within 14 days | 100% of legal n by laws provided within 14 days by June 2021 | Legal opinion Register | Q3 | 14 days of request | 14 days of request | Operational |  | N/A | N/A | Legal opinion Register
Turnaround time for development of service level agreements upon request | 100% of Service level agreement developed within 14 days by June 2021 | 100% of Service level agreement developed within 14 days | Q3 | 14 days of request | 14 days of request | Operational |  | N/A | N/A | Service level agreements register
2021/2022 Draft IDP and approved by Council | 2021/2022 Draft IDP and approved by Council by March 2020 | 2020/2021 Draft IDP | Q3 | Approved 2020/2021 Draft IDP | Approved 2020/2021 Draft IDP | Operational |  | N/A | N/A | Council Resolution
2021/2022 Final IDP approved by Council | 2021/2022 Final IDP approved by Council by May 2020 | 2020/2021 Amended IDP | Q3 | Approved 2020/2021 IDP | Approved 2020/2021 IDP | Operational |  | N/A | N/A | Council Resolution
2020/2021 IDP,PMS and Budget process plan and approved by Council | 2020/2021 IDP,PMS and Budget process plan and approved by Council byAugust 2020 | 2019/2020 Approved Process Plan | Q3 | Approved Process Plan | Approved Process Plan | Operational |  | N/A | N/A | Council Resolution
Number IDP public participation meetings held | Number IDP public participation meetings held by June 2021 | 2019/2020 IDP public participation meetings | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Number of IDP June 2021 | Number of IDP June 2021 | 2019/2020 IDP representative forums | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Risk Management Strategy approved by council | Risk Management Strategy approved by council by June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Risk Management Policy approved by council | Risk Management Policy approved by council June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Prevention of Fraud & Corruption Policy approved by council | Prevention of Fraud & Corruption Policy approved by council by June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Fraud Prevention Strategy approved by council | Fraud Prevention Strategy approved by council by June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Whistle-blowing Policy approved by council | Whistle-blowing Policy approved by council | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Risk Identification & Assessment conducted | Risk Identification & Assessment conducted by June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Risk Mitigation Plan/Treatment Plan developed by June 2021 | Risk Mitigation Plan/Treatment Plan developed by June 2021 | New | Q3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A