## forewords
Moses Kotane Local Municipality
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
BID No. 024/MKLM/2021/2022 | [6 empty] | Date : 01/12/2021
SCHEDULE OF QUANTITIES
Preamble to Pricing the Schedule of Quantities
1 | The Conditions of Contract, the Special / Particular Conditions of Contract, the Specifications, (including
the Project and Particular Specifications) and the Drawings are to be read in conjunction with this
Schedule of Quantities.
2 | The Schedule of Quantities comprises items covering the Contractor's profit and costs of general liabilities
and of the construction of temporary and permanent works.
3 | The Tenderer is at liberty to insert a rate of his own choosing for each item in the Schedule of Quantities
and his attention is drawn to the fact that the Contract has the right under various circumstances, to
payments for additional works carried out and that the Engineer shall base his assessment of the rates to
be paid for such additional work on appropriate rates inserted in the Schedule by the Contractor.
4 | Clause 8 of each Standardized Specification and the measurement and payment clause of each Particular
Specification, read together with the relevant clauses of the Project Specification, set out what ancillary
or associated activities are included in the rates for operations specified.
5 | Descriptions in the Schedule of Quantities of this Tender Document drawn up generally in accordance with
the latest issue of Civil Engineering Quantities (1). Should any requirement of the measurement and
payment clause of the applicable Standardized Specification (2), or the Project Specification(2), or the
Particular Specification (2) conflict with the terms in the Schedule of Quantities in this Tender Document the
requirements in the Schedule of Quantities in this tender document shall prevail. The Contractor's attention
will be called upon Clause "Qualifications of Tenders" and Clause "Preliminary & General" in the section
"Conditions of Tender" in this Tender Document
Unless otherwise stated, items are measured nett in accordance with the Drawings, and no allowance has
been made for waste. The Tender Quantities are derived from preliminary drawing, so due allowance shall
be made for possible changes.
6 | The prices and rates to be inserted in the Schedule of Quantities are to be the exclusive prices to the
Employer for the work described under the various items. Such prices shall cover all costs and expenses that
may be required in and for the construction of the work described, and shall cover the cost of all general
risks, liabilities and obligations se forth or implied in the document an which the Tender is based. The prices
and rates specified in the Schedule of Quantities for this Contract shall be fixed, final and binding throughout
the Contract period.
7 | A price, rate or the word "NIL" is to be entered against each item of the Schedule of Quantities, whether the
quantities are stated or not. If no rate is entered against an Item or a word other than "NIL" is entered, the
item will be considered to be covered by other rates in the Schedule, the rate will, nevertheless be taken as
"NIL" and no claim will be considered if the quantity of such item increases or decreases.
The Tenderer shall price each item in the Schedule of Quantities in BLACK INK and each item must be priced
separately and not in combination with other items (no groupings shall be allowed).
The Contractor is not entitled to change wording and / or quantities in the Schedule of Quantities without
the written permission of the Engineer.
8 | Units of measurement stated in the Schedule of Quantities are all metric units.
Abbreviations used are as follows:
| mm | = | millimeter
| m | = | meter
| km | = | kilometer
| km-pass | = | kilometer pass
| m² | = | square meter
| m²-pass | = | square meter pass
| m³ | = | cubic meter
| m³-km | = | cubic meter-kilometer
| ha | = | hectare
| kw | = | kilowatt
| l | = | liter
| kl | = | kilolitre
| kg | = | kilogram
| t | = | ton (1 000 kg)
| Prov. | = | provisional amount
| m³ km | = | cubic meter-kilometer
| % | = | percent
Contractor |  |  | Witness 1 | Witness 2 | Employer | Witness 1 |  | Witness 2
| PC Sum | = | prime cost sum
| Sum | = | sum
| No. | = | number
All rates and amounts quoted in the Schedule of Quantities shall be in South African Rand
9 | The Tenderer must provide a rate for all items marked "Rate only" in the amount column. The reason for this is
that even though no work is expected to be done under such item, the stated rate shall be applied if any
work should be necessary under that particular item.
Notes :
1) | The standard system of measurement of civil engineering quantities for South Africa published by the South
African Institution of Civil Engineers.
2) | See definition in Sub-Clause 2.1 of Part 1 of SANS 0120.
Information for the Submission of the Schedule of Quantities for Certifications
1) | At each and every item where a reference is made for the quantities to be recorded in the site instruction book
by the Engineer's representative and those signed and dated records must be forwarded with the relevant
certificates for payments. Failing to do so will annul those items with the result that the requested quantities
and amounts shall be deleted from the payment certificates and no compensation shall be made for such items.
2) | For each "Provisional Sum" items proof of transaction (i.e.. Proof of payment) must accompany the relevant
payment certificates. Failing to do so will result in no compensation being made for such items. Purchase invoice
or delivery note is insufficient proof of payments.
3) | For each item that is claimed in the section "Materials on site" proof of payment and / or ownership by the
Claimant must accompany the relevant payment certificates. Failing to do so will result in no compensation
being made for such items. Purchase invoice or delivery note is insufficient proof of payment. A form is available
in the Tender Document for proof of ownership of materials which page (or copy of that page) can be signed
and proof stamped by the supplier, stating the value of purchased goods. The Engineer requires a copy of the
receipt as proof of ownership of the materials claimed in the certificate.
4) | Under no circumstances will allowance be made to deviate from the specifications set out in the Tender
Document without the written consent of the Engineer. Any contravention of this shall result in rectification by
the Contractor at his own cost.
Contractor |  |  | Witness 1 | Witness 2 | Employer | Witness 1 |  | Witness 2

## works
BID No. 024/MKLM/2021/2022 | [5 empty] | Date : 01/12/2021
Moses Kotane Local Municipality |  |  |  | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Moses Kotane Local Municipality
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
122
Contractor | Witness 1 | Witness 2 | Employer |  | Witness 1 |  | Witness 2

## pg1
BID No. 024/MKLM/2021/2022 | [9 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [6 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment |  | Item Description |  |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [10 empty] | Rands/cents
| SANS |  | Schedule 1
| 1200 | LIC | Preliminary and General
A,AB
1.1 |  |  | Fixed Charge Items
A
1.1.1 | 8.3.1 |  | Contractual requirements to cover the Contractor's costs for the providing of sureties, |  |  |  |  | sum | 1
insurances and other requirements as stated in the Tender Document
1.1.2 |  |  | The Contractor to establish facilities on site as follows :
1.1.2.1 | PSAB 1 |  | The Contractor to provide a name board as detailed in the Tender Document |  |  |  |  | No | 1
(DRW 006NB-04)
1.1.2.2 | PS 7.1 |  | Provide an office : furnished room complete described in SANS 1 200 AB, item 3.2, 4.1 |  |  |  |  | No | 1
| PSAB 2 |  | and 5.2, alternatively as requested in the Tender Document
1.1.2.3 | PSAB 5 |  | The Contractor to provide survey equipments for the use of the Engineer and / or his |  |  |  |  | sum | 1 |  |  | Rate only
representative as set out in the Tender Document in Clause PSAB 5 failing to do so the
Engineer reserves the right to purchase such equipment to the cost of the Contractor
( i.e.. deduct such amounts from the Contractor's payment certificates )
1.1.3 |  |  | Facilities for the Contractor for the duration of the Contract :
1.1.3.1 | PS 6.1 |  | Provide offices and storage sheds as necessary for the duration of the Contract |  |  |  |  | sum | 1
1.1.3.2 | PS 6.1 |  | Provide workshops for the duration of the Contract |  |  |  |  | sum | 1
1.1.3.3 | PS 6.4 |  | Provide living accommodations for the Contractor and his employees |  |  |  |  | sum | 1
1.1.3.4 | PS 6.5 |  | Provide ablution and latrine facilities as specified in the Tender Document |  |  |  |  | sum | 1
1.1.3.5 | PS 6.1 |  | Supply tools and equipments as per the Contractor's requirements |  |  |  |  | sum | 1
1.1.3.6 | PS6.2&6.3 |  | Provide water supplies, electric power and communications as necessary |  |  |  |  | sum | 1
1.1.3.7 | 5.5 |  | Deal with water as described in SANS 1 200 A section 5.5 |  |  |  |  | sum | 1
1.1.3.8 |  |  | The Contractor to establish access road to site ( Sub Clause 5.8 in SANS 1 200 A), |  |  |  |  | sum | 1
further clarified in PSA 6 in the Tender Document
1.1.3.9 | 8.3.3 |  | Other fixed charge obligations by the Contractor that are relevant to the successful |  |  |  |  | sum | 1
completion of the Contract
1.1.4 | 8.3.4 | LI | The Contractor to remove Engineer's and Contractor's site establishment upon |  |  |  |  | sum | 1
completion of the Contract
1.2 |  |  | Time Related Items
A
1.2.1 |  |  | Contractual requirements to cover the Contractor's costs for the providing of sureties, |  |  |  |  | sum | 1
insurances and other requirements as stated in the Tender Document
1.2.2 |  |  | Operate and maintain facilities on site as follows :
1.2.2.1 |  | LI | a.) Facilities for the Engineer and for his representative for the duration of Contract |  |  |  |  | sum | 1
as stated in item 1.1.2.1 through 1.1.2.3
1.2.2.2 |  | LI | b.) Facilities for the Contractor for the duration of the Contract as stated in items |  |  |  |  | sum | 1
1.1.3.1 through 1.1.3.9
1.2.3 |  |  | Supervision as specified in the SANS 1 200 A, the Contractor's attention will be called |  |  |  |  | sum | 1
to the Clause dealing with the " Site Supervision " in the " Conditions of Tender "
section in the Tender Document
1.2.4 |  |  | The Contractor's company and head office overhead costs |  |  |  |  | sum | 1
1.2.5 |  |  | Other time related obligations by the Contractor that are relevant to the |  |  |  |  | sum | 1
successful completion of the Contract
Total carried forward
123
Contractor |  |  |  | Witness 1 | Witness 2 | Employer |  | Witness 1 |  |  | Witness 2

## pg2
BID No. 024/MKLM/2021/2022 | [8 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [5 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment | Item Description |  |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [9 empty] | Rands/cents
| SANS | Schedule 1 ( Continued )
| 1200 | PRELIMINARY AND GENERAL
A,AB
123
1.3 |  | Provisional Sums by the Engineer
A
1.3.1 |  | Provisional sum for various tests requested by the Engineer or his representative |  |  |  |  | Prov | 1 | 25000 |  | 25000
in the site instruction book, where the date, position, nature and costs of such
tests must be recorded and a copy must accompany the Contractor's
certificate for payment purposes
1.3.2 |  | Contractor's overhead and profit on Item 1.3.1 |  |  |  |  | %
1.3.3 | PSA15.2 | Provisional sum for the remunuration of the CLO, for each village or as per Client's |  |  |  |  | Prov | 1 | 28000 |  | 28000
instructions.
1.3.4 | PSA15.2 | Contractor's overhead and profit on Item 1.3.3 |  |  |  |  | %
1.3.5 | PSA14.3 | Provisional sum for the Sitting Allowance of the PSC Members attending Site Meetings |  |  |  |  | Prov | 1 | 20000 |  | 20000
during the Construction Phase
1.3.6 | PSA14.3 | Contractor's overhead and profit on Item 1.3.5 |  |  |  |  | %
Total carried to summary
124
Contractor |  |  | Witness 1 | Witness 2 | Employer |  | Witness 1 |  |  | Witness 2

## pit1
BID No. 024/MKLM/2021/2022 | [8 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [6 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment |  | Item Description |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [9 empty] | Rands/cents
| SANS |  | Schedule 2
| 1 200 | LIC | Earth Works and Pit Linning
Drawing refers : 006UD-02, UD-03 & VIP-05
2.1 |  |  | Site Clearance
C
2.1.1 | 8.2.1 |  | Clear vegetation, rubble, bushes and trees up to 1 m of girth to an area of 8.2 m² |  |  |  | m² | 1053 |  |  | Rate Only
| PSC 1-4 |  | 3000 x 2740 mm
2.2 |  |  | Excavations
D
2.2.1 | PSD 8.3.3 |  | Excavate the pit at the task rate with consideration of work space |  |  |  | m³ | 1053
and risk of collapse of sides of toilet pit.
size 3.000m x 2.740m X 1m deep and keeping trench excavations free of all
water - inclusive of foundations required
2.2.2 | PSD 8.3.3b |  | Extra Over Item 2.2.1 for Excavation in
| PSD 8.3.3b |  | a) Intermediate material |  |  |  | m³ | 52.65
| PSD 8.3.3b |  | b) Hard Rock |  |  |  | m³ | 52.65
2.2.3 |  | LI | Backfill spread balance of soil and compact around built structure in layers of 200mm, |  |  |  | m³ | 52.65
to NGL. Ref attached drawings.
2.2.5 | POHS10.15 & |  | Safeguarding Excavation in terms of OSH Act to prevent people and |  |  |  | Sum | 1
| POHS10.16 |  | Animals from falling into pit.
2.3 |  |  | Excavation Ancillary Items
2.3.1 |  |  | Make up deficiency in backfill material due to spoiling of surplus and unsuitable |  |  |  | m3 | 15.795
material from other necessary excavations on site within free haul distance,
(compaction of this material measured in excavation items ),
2.3.2 |  |  | Make up deficiency in backfill material due to spoiling of surplus and unsuitable |  |  |  | m3 | 26.325 |  |  | Rate Only
material from designated borrow pits on site within free haul distance, (compaction
of this material measured in excavation items ),
2.3.3 |  |  | Open up borrow pit if requested by the Engineer following the specifications in SANS |  |  |  | sum | 1 |  |  | Rate Only
1 200
2.4 |  |  | Dealing with Existing Services
DB
2.4.1 | 8.3.5.a | LI | Excavate by hand in soft material to expose existing services crossing the trenches/pit |  |  |  | Sum | 1 |  |  | Rate Only
| PS 8.1 |  | and provide permanent or temporary protection
2.4.2 |  | LI | Unforeseen services on site such as cables and pipes to which no record of |  |  |  | Sum | 1 |  |  | Rate Only
their existance was provided or not shown on record drawings.
2.5 |  |  | Pit/Sub-Structure
PA1.2
2.5.1 |  |  | 250 MICRON IN THE PIT
|  |  | Prepare bottom of Pit, Compact to 93% MOD AASHTO, Insert/lay the 250 MICRON inside the pit |  |  |  | No | 130
The MICRON to fit inside the pit to all four corners
The insertion of the MICRON must be done with extreme caution to ensure that is not damaged or torn
2.5.2 |  |  | PIT LINING - ASSEMBLING OF BOTTOM STRUCTURE
|  | LI | Assembling of pit lining out of supplied precast concrete panels consisting of short |  |  |  | No | 130
beams, long beams, side panels, end panels, divider panels and upright beams.
2.5.3 |  |  | TOP STRUCTURE
|  | LI | Erect/assemble and fix supplied Top structure including but not limited to: fitment of pan, |  |  |  | No | 130
ventilation pipe, extraction unit, Roof & door.
Including cement seal between bottom and top structure
2.5.4 | PA 1.2.1 | LI | BOTTOM &TOP STRUCTIRE
2.5.4.1 |  |  | Distribute top and bottom structures to households |  |  |  | No | 130
Total carried forward
125
Contractor |  |  |  | Witness 1 | Witness 2 | Employer | Witness 1 |  |  | Witness 2

## top structure
BID No. 024/MKLM/2021/2022 | [9 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [6 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment |  | Item Description |  |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [10 empty] | Rands/cents
| SANS |  | Schedule 3
| 1 200 | LIC | Supply & Erect Top Structure
Drawing refers : 006UD-02, UD-03 & VIP-05
2.6 |  |  | Provision of Top structure on Site
PRECAST TOP STRUCTURE (ELDOCRETE)
2.6.1 | PA 1.2.1 | LI | Provisional Sum for the supply of the pre-cast top structure, completely manufactured, |  |  |  |  | No | 130 | 5430 |  | 705900
including, but not limited to a Pit Cover Slab, floor inserts, walls, roof, lockable door,
Vent Pipe & Fly Screen, pedestal, seat and lid, handwash facility and urine
components.
(Top Structures to be Purchased by the Municipality directly from their
Nominated Subcontractor)
2.6.1.1 |  |  | Contractor's overhead and profit on Item 2.6.1 |  |  |  |  | %
2.6.2 |  |  | PRECAST BOTTOM STRUCTURE (ELDOCRETE)
| PA 1.2.1 | LI | Provisional Sum for the supply of the pre-cast bottom structure, completely |  |  |  |  | No | 130 | 3800 |  | 494000
manufactured, including, but not limited to side panels, end panels, divider panels,
short beams, long beams, upright beams components INCLUDING 250 Micron HDPE pit
liner and grid (x 2)
(Bottom Structures to be Purchased by the Municipality directly from their
Nominated Subcontractor)
2.6.2.1 |  |  | Contractor's overhead and profit on Item 2.6.2 |  |  |  |  | %
2.6.3 |  |  | URINE DIVERSION
2.6.3.1 |  |  | Supply 19mm Crusher Stone |  |  |  |  | m³ | 16.25
2.6.3.2 |  |  | Supply A4 Non Woven Polyester Bidim |  |  |  |  | m² | 143
2.6.3.3 |  |  | Connect/Fit, lay and backfill the 20mm Ø HDPE Drain pipe to the toilet sloping to the |  |  |  |  | No | 130
0.5x 0.5x 0.5m french drain at a slope of 1:15
Ref attched Drawings (006UD -02 and 006UD-03)
2.6.4 |  |  | CLEARING SITE
2.6.4.1 |  |  | Clear site, rake it neat and discard excess material |  |  |  |  | No | 130
Total carried to summary
126
Contractor |  |  |  | Witness 1 | Witness 2 | Employer |  | Witness 1 |  |  | Witness 2

## ohs
BID No. 024/MKLM/2021/2022 | [8 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [5 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment | Item Description |  |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [9 empty] | Rands/cents
| SANS | Schedule 4
| 1 200 | Occupational health and safety requirements
4.1 |  | Notification of construction work
4.1.1 |  | Allow for the costs on notification of the Provincial Director of construction |  |  |  |  | sum | 1
work Regulation 3
4.2 |  | Program
4.2.1 | PS10.5 | Allow for the costs on setting up a Health and Safety Program including a file on |  |  |  |  | sum | 1
| PR10.32 | site, Regulations 3 and 5 - Include the cost to compile the following documents :
| 1 | Copy of H & S Act 85 of 1993 including Construction Regulations July 2003
| 2 | Copy of tender document
| 3 | Copy of drawings
| 4 | Notification of construction work
| 5 | Letters of appointment
| 6 | Company safety Policy
| 7 | Company organogrammme
| 8 | Notice in respect of machinery
| 9 | Ten commandments of safety
| 10 | Emergency telephone numbers
| 11 | List of subcontractors
| 12 | Proof of registration with COID Insurer
| 13 | Training material
| 14 | Risk assessments and method statements
| 15 | Registers as specified elsewhere
| 16 | Safe work procedures
NOTE:
The file shall be a lever arch file with original color document of acceptable standards
The file will be expanded during the project as and when required by the Client
4.3 |  | Supervisory appointments
4.3.1 |  | Allow for the costs of a person to carry out a risk assessment |  |  |  |  | sum | 1
4.3.2 |  | Allow for the appointment of a SHE Coordinator to do monthly inspections |  |  |  |  | sum | 1
(Control on SHE Representative provisional sum for seven months)
4.3.3 |  | Allow for the appointment of a H & S Induction trainer provisional sum for |  |  |  |  | sum | 1
construction period.
4.3.4 |  | Allow for the costs of setting up safe works procedures by a competent person |  |  |  |  | sum | 1
4.4 |  | Training courses
4.4 |  | Allow for the cost of setting up training courses
The following provisional sums are allowed for each training course
PHASE 1 :
4.4.1 |  | Toolbox talks on functions of the SHE |  |  |  |  | No | 1
4.4.2 |  | Representative |  |  |  |  | No | 1
4.4.3 |  | Induction training |  |  |  |  | No | 1
4.4.4 |  | Community training |  |  |  |  | No | 1
4.4.5 |  | Toolbox talks on environmental awareness |  |  |  |  | No | 1
PHASE 2 :
4.4.6 |  | Training on construction vehicles and mobile plant |  |  |  |  | No | 1
4.4.7 |  | First aid awareness |  |  |  |  | No | 1
4.4.8 |  | Fire fighting awareness |  |  |  |  | No | 1
4.4.9 |  | HIV training | [5 empty] | 0
4.4.10 |  | Tool box talks on hand tools and hand tool accidents |  |  |  |  | No | 1
4.4.11 |  | Tool box talks on machine guarding
4.4.12 |  | Tool box talks on lifting materials by hand |  |  |  |  | No | 1
4.4.13 |  | Tool box talks on safe loading |  |  |  |  | No | 1
4.4.14 |  | Tool box talks on safety signs |  |  |  |  | No | 1
4.4.15 |  | Tool box talks on ten commandments of safety |  |  |  |  | No | 1
4.5 |  | SHE representative
Allow for the following appointments to be part of the functions of SHE
Representative
4.5.1 |  | Allow for the appointment of a SHE representative to be permanently on site |  |  |  |  | sum | 1
Total carried forward
127
Contractor |  |  | Witness 1 | Witness 2 | Employer |  | Witness 1 |  |  | Witness 2

## ohs2
BID No. 024/MKLM/2021/2022 | [8 empty] | Date : 01/12/2021
Moses Kotane Local Municipality | [5 empty] | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment | Item Description |  |  |  |  | Unit | Quantity | Rate |  | Amount
No. | Refers | [9 empty] | Rands/cents
| SANS | Schedule 4 (continued)
| 1 200 | Occupational health and safety requirements
127
4.5.2 |  | Accident investigator - allow for the appointment of an accident investigator |  |  |  |  | sum | 1
4.5.3 |  | Construction vehicle and mobile plant inspector - allow for the appointment of a |  |  |  |  | sum | 1
full time inspector of construction vehicles
4.5.4 |  | Hand tool inspector - allow for the appointment of a full time hand tool inspector |  |  |  |  | sum | 1
4.5.5 |  | Portable electrical equipment inspector - allow for the appointment of a full time |  |  |  |  | sum | 1
inspector of portable electrical equipments
4.5.6 |  | Stacking and storage inspector - allow for the costs of a competent person to |  |  |  |  | sum | 1
supervise all stacking and storage
4.5.7 |  | Hygiene and facility inspector - allow for the appointment of a full time hygiene |  |  |  |  | sum | 1
and facility Inspector
4.5.8 |  | Fire equipment inspector - allow for the costs of a competent person to inspect |  |  |  |  | sum | 1
all fire equipment
4.5.9 |  | First aid box inspector - allow for the costs of a competent person to inspect first |  |  |  |  | sum | 1
aid box
Allow for the following appointments of personnel with responsibilities towards
Health and Safety
4.5.10 |  | Allow for the appointment of full time employees as construction supervisors |  |  |  |  | sum | 1
4.5.11 |  | Allow for the appointment of full time excavation inspector for excavation of |  |  |  |  | sum | 1
more than 1.2 m deep
4.5.12 |  | Allow for the appointment of full time employee to act as community liaison |  |  |  |  | sum | 1 |  |  | Rate only
4.6 |  | Fire fighting equipment
4.6.1 |  | Provide 3 kg fire fighting equipment suitable for electric fires on each site |  |  |  |  | No | 1
4.6.2 |  | Obtain inspection certificate of fire fighting equipment |  |  |  |  | No | 1 | 750
4.7 |  | First aid
4.7.1 |  | Allow for the cost of a basic First Aid Kit and stretcher |  |  |  |  | No | 1
4.8 |  | Personal protective clothing
Allow for the cost of personal protective clothing as follows :
4.8.1 |  | Safety Gloves |  |  |  |  | No | 50
4.8.2 |  | Safety Shoes |  |  |  |  | No | 50
4.8.3 |  | Gum Boots |  |  |  |  | No | 10
4.8.4 |  | Dust Masks |  |  |  |  | No | 1000
4.8.5 |  | Overalls |  |  |  |  | No | 50
4.8.6 |  | Hard Hats |  |  |  |  | No | 10 |  |  | Rate only
4.9 |  | COVID-19 COMPLIANCE
4.9.1 |  | Covid 19 OHS Plan, HIRA and file |  |  |  |  | No | 1
4.9.2 |  | Hand washing Facilities |  |  |  |  | No | 2
4.9.3 |  | Personal Protective Equipment
|  | Cloth mask |  |  |  |  | No | 50
|  | Hand gloves surgical plastic |  |  |  |  | No | 50 |  |  | Rate only
|  | Face shield |  |  |  |  | No | 3
4.9.4 |  | Supply Sanitizer foot press stand |  |  |  |  | No | 2
Total carried to summary
128
Contractor |  |  | Witness 1 | Witness 2 | Employer |  | Witness 1 |  |  | Witness 2

## ohs3
BID No. 024/MKLM/2021/2022 | [6 empty] | Date : 01/12/2021
Moses Kotane Local Municipality |  |  |  |  | Project No. :MKLM/RSP/21_03
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
Item | Payment | Item Description |  |  |  | Unit | Quantity | Rate | Amount
No. | Refers | [7 empty] | Rands/cents
| SANS | Schedule 4 (continued)
| 1 200 | Occupational health and safety requirements
0
4.9.5 |  | Supply Sanitizers for the duration of Contract |  |  |  | sum | 1
4.9.6 |  | Supply Tissue for hand wiping for the duration of the Contract |  |  |  | sum | 1
4.9.7 |  | Bio Hazardous Waste bins - (the colour coded ones) |  |  |  | No | 2
4.9.8 |  | Transportation of the disposal of the Bio-hazardous waste |  |  |  | sum | 1
4.9.9 |  | Cleaning detergents, Cleaning cloth and cleaning equipments |  |  |  | sum | 1
4.9.10 |  | Screeing Equipment digital body thermometer infrared non-contact |  |  |  | No | 1
4.9.11 |  | Covid-19 Compliance Officer |  |  |  | No | 1
4.9.12 |  | Provide an Isolation room |  |  |  | No | 1
Total carried to summary
129
Contractor |  |  | Witness 1 | Witness 2 | Employer | Witness 1

## Summary
Moses Kotane Local Municipality
SUPPLY AND INSTALLATION OF 130 VIDP TOILETS IN MABELEAPODI THROUGH RURAL SANITATION PROGRAMME
BID No. 024/MKLM/2021/2022 |  |  |  | Date : 01/12/2021
Summary of the Schedule of Quantities
Tendered Amounts
Schedule 1 | Preliminary and General
Schedule 2 | Earth Works and Pit Linning
Schedule 3 | Supply & Erect Top Structure
Schedule 4 | Occupational health and safety requirements
Total construction value
Add estimated (5% of construction value) contingencies
Total construction and contingency value
Add 15% Value Added Tax
Total value carried to Total Summary Page | [6 empty] | 0
130
Contractor | Witness 1 | Witness 2 | Employer | Witness 1 |  | Witness 2