## PnGs
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200A | SECTION A: PRELIMINARY & GENERAL
A.1 | 8.2.1 and 8.3 | FIXED-CHARGE ITEMS
A.1.1 | 8.3.1 | Contractual Requirements |  | Sum | 1
A.1.2 | PSA 8.3.5 | For compliance with Health and Safety Act 2003 and Construction Regulations 2014 and the Health and Safety Specification |  | Sum | 1
A.1.3 | PSA 8.3.6 | For compliance with the National Environmental Management Act 1998 and the Environmental Management Plan |  | Sum | 1
A.1.4 |  | Submission of the Environmental Management Plan(PES SPEC) |  | Sum | 1
A.1.5 |  | Submission of Quality Control and Quality Assurance File(OHS SPEC) |  | Sum | 1
A.1.6 | 8.3.2 | Establish Facilities on the Site :
| 8.3.2.1 | Facilities for Engineer (SANS 1200 AB)
A.1.6.1 |  | a) Furnished Office (PSAB 3.2) |  | Sum | 1
A.1.6.2 |  | b) Nameboards |  | Sum | 1
A.1.6.3 |  | c) Telephone |  | Sum | 1
A.1.6.4 | PSAB 8.3.2.1 | d) Carports |  | Sum | 1
A.1.6.5 | PSAB 8.3.2.1 | e) Laptop (PSAB 3.5) |  | Sum | 1 | 20000 | 20000
A.1.6.6 | PSAB 8.3.2.1 | f) Printer (PSAB 3.6) |  | Sum | 1
A.1.6.7 | PSAB 8.3.2.1 | g) Photocopy facilities (PSAB 3.7) |  | Sum | 1
A.1.6.8 | PSAB 8.3.2.1 | h) Survey equipment (PSAB 5.6) |  | Sum | 1
SUB-TOTAL CARRIED FORWARD
|  | brought forward |  |  |  |  | 0
| 8.3.2.2 | Facilities for Contractor
A.1.6.9 |  | a) Offices and storage sheds |  | Sum | 1
A.1.6.10 |  | b) Workshops |  | Sum | 1
A.1.6.11 |  | e) Ablution and latrine facilities |  | Sum | 1
A.1.6.12 |  | f) Tools and equipment |  | Sum | 1
A.1.6.13 |  | g) Water supplies, electric power and communications |  | Sum | 1
A.1.6.14 |  | h) Dealing with water (Subclause 5.5) |  | Sum | 1
A.1.6.15 |  | i) Access (Subclause 5.8) |  | Sum | 1
A.1.6.16 |  | j) Plant |  | Sum | 1
A.1.6.17 |  | k) Equipment for testing compaction densities with radio-active method (troxler or similar approved) |  | Sum | 1
A.1.6.18 |  | k) Setting out of all works and As-Builts |  | Sum | 1
A.1.6.19 | 8.3.3 | Other fixed-charge obligations |  | Sum | 1
A.1.6.20 | 8.3.4 | Remove Engineer's and Contractor's Site establishment on completion |  | Sum | 1
A.2 | 8.2.2 and 8.4 | TIME-RELATED ITEMS
A.2.1 | 8.4.1 | Contractual Requirements |  | Sum | 1
A.2.2 | PSA 8.4.6 | For compliance with Health and Safety Act 2003 and Construction Regulations 2014 and the Health and Safety Specification |  | Sum | 1
A.2.3 | PSA 8.4.7 | For compliance with the National Environmental Management Act 1998 and the Environmental Management Plan |  | Sum | 1
SUB-TOTAL CARRIED FORWARD | [6 empty] | 0
|  | brought forward |  |  |  |  | 0
A.2.4 | 8.4.2 | Operate and maintain facilities on the Site:
| SANS 1200 AB | Facilities for Engineer for duration of construction (SABS 1200 AB)
A.2.4.1 |  | a) Furnished Office (PSAB 3.2) |  | Sum | 1
A.2.4.2 |  | b) Nameboards |  | Sum | 1
A.2.4.3 |  | c) Telephone |  | Sum | 1 | 20000 | 20000
|  | Overherads, charges and profits on A.2.4.3 above. |  | % | 20000
A.2.4.4 | PSAB 8.4.2.1 | d) Carports |  | Sum | 1
A.2.4.5 | PSAB 8.4.2.1 | e) Laptop (PSAB 3.5) |  | Sum | 1 | 30000 | 30000
|  | Overherads, charges and profits on PSAB 8.4.2.1 above. |  | % | 30000
A.2.4.5 | PSAB 8.4.2.1 | f) Printer (PSAB 3.6) |  | Sum | 1
A.2.4.6 | PSAB 8.4.2.1 | g) Photocopy facilities (PSAB 3.7) |  | Sum | 1
A.2.4.7 | PSAB 8.4.2.1 | h) Survey equipment (PSAB 5.6) |  | Sum | 1
| 8.4.2.2 | Facilities for Contractor for duration of construction, except where otherwise stated
A.2.4.8 |  | a) Offices and storage sheds |  | Sum | 1
A.2.4.9 |  | b) Workshops |  | Sum | 1
A.2.4.10 |  | e) Ablution and latrine facilities |  | Sum | 1
A.2.4.11 |  | f) Tools and equipment |  | Sum | 1
A.2.4.12 |  | g) Water supplies, electric power and communications |  | Sum | 1
A.2.4.13 |  | h) Dealing with water (Subclause 5.5) |  | Sum | 1
A.2.4.14 |  | i) Access (Subclause 5.8) |  | Sum | 1
A.2.4.15 |  | j) Plant |  | Sum | 1
A.2.4.16 | 8.4.3 | Supervision |  | Sum | 1
SUB-TOTAL CARRIED FORWARD
brought forward
A.2.4.17 | 8.4.4 | Company and head office overhead costs |  | Sum | 1
A.2.4.18 | 8.4.5 | Other time-related obligations personnel |  | Sum | 1
A.2.4.19 | 8.4.5 | Provision of Security Personnel |  | Sum | 1
A.2.4.20 |  | Provision of full-time construction safety officer(OHS SPEC) |  | Sum | 1
A.3 | 8.5 | SUMS STATED PROVISIONALLY BY ENGINEER
A.3.1 | PSA 8.5 c)(1) | Testing carried out by commercial laboratories |  | Prov Sum | 1 | 75000 | 75000
A.3.2 | PSA 8.5 c)(2) | Protection and Relocation of Existing Services, including wayleaves |  | Prov Sum | 1 | 50000 | 50000
A.3.3 | PSA 8.5 c)(3) | Dealing with bad founding Conditions. |  | Prov Sum | 1 | 200000 | 200000
A.3.4 | PSA 8.5 c)(4) | Soft and hardscaping as identified by by Engineer/ Client. |  | Prov Sum | 1 | 50000 | 50000
A.3.4 | PSA 8.5 c)(5) | Accomodadation of the Resident Engineer |  | Prov Sum | 1 | 240000 | 240000
A.3.5 | PSA 8.5 c)(5) | Overherads, charges and profits on A.3.1 to A.3.4 above. |  | % | 540000
A.4 | 8.6 | PRIME COST ITEMS
A.4.1 | PSA 8.6(e) | Allowance Community Liaison Officer (CLO) & Steering Committee Members (SCM’s) |  | Prov Sum | 1 | 50000 | 50000
A.4.2 |  | Charges on profit on item A.4.1 above |  | % | 50000
SUB-TOTAL CARRIED FORWARD
|  | brought forward |  |  |  |  | 0
A.5 | 8.7 | DAYWORKS
A.5.1 |  | a) Labour:
A.5.1.1 |  | (i) Unskilled Labourer |  | h | 1 |  | Rate Only
A.5.1.2 |  | (ii) Semi-skilled Labourer: pipe layer, section leader, etc. |  | h | 1 |  | Rate Only
A.5.1.3 |  | (iii) Skilled Artisan |  | h | 1 |  | Rate Only
A.5.2 |  | b) Plant and Equipment:
A.5.2.1 |  | (i) Tractor Loader Backhoe (min 45kW) |  | h | 1 |  | Rate Only
A.5.2.2 |  | (ii) Hand vibration compactor (0,5 t) |  | h | 1 |  | Rate Only
A.5.2.3 |  | (iii) 1 Ton Pick-up Truck |  | h | 1 |  | Rate Only
A.5.2.4 |  | (iii) Tipper Truck (6 m3) |  | h | 1 |  | Rate Only
A.5.2.5 |  | (iv) Tractor + Trailer (trailer type 5000 m3) |  | h | 1 |  | Rate Only
A.5.2.6 |  | (v) Water tanker (Trailer type: 6000 liters minimu) |  | h | 1 |  | Rate Only
A.5.2.7 |  | (vi) Excavator |  | h | 1 |  | Rate Only
A.5.2.8 |  | (vii) Gradder |  | h | 1 |  | Rate Only
A.5.2.9 |  | (viii) Generator |  | h | 1 |  | Rate Only
TOTAL CARRIED FORWARD TO SUMMARY | [6 empty] | 0

## Site Clearance
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SECTION B: SITE CLEARANCE
B.1 |  | SITE CLEARANCE
B.1.1 | 8.2.1 and PSC 8.2.1 | Clear and grub, including removal of all trees and stumps of girth 0m to 1m in the way. The girth shall be measure at the narrowest point of the tree or stump in the first metre of its height above ground level as per SANS1200C Clause 8.2.2 | LI | m2 | 15000
B.1.1.1 | 8.2.1 and PSC 8.2.1.1 | Clear and grub of Existing Channels, including removal of all trees and stumps of girth 0m to 1m in the way. The girth shall be measure at the narrowest point of the tree or stump in the first metre of its height above ground level as per SANS1200C Clause 8.2.2 | LI | m2 | 2000
B.1.2 | PSC 8.2.2 | Fell, remove and grub all trees and tree stumps of Girth
B.1.2.1 |  | (a) Over 1m and up to and including 2m. | LI | No. | 12
B.1.2.2 |  | (b) over 2m and up to and including 3m | LI | No. | 4
B.1.3 | 8.2.5 | Take down existing fences where directed by the Engineer | LI | km | 1
B.1.4 | PSC 8.2.9 | Transport materials and debris to unspecified sites and dump (Provisional) |  | m3.km | 8000
B.1.5 |  | Removal of existing culverts portal Culvert and disposig off site |  | Sum | 1 |  | Rate Only
FENCING
B.1.8 | PSC 8.2.5 | Supply and erect new fencing material for new fences and for supplementing material in existing fences which are being repaired or removed:
|  | (i) instalation of new diamond mesh | LI | km | 5
B.1.8.1 |  | (ii) Re-instate previously removed fence with the stored material | LI | km | 1
B.1.8.3 | PSC 8.2.5 | (ii) New gates (size and type Indicated)
|  | (ii.1) Double leaf vehicle | LI | No | 6
TOTAL CARRIED FORWARD TO SUMMARY
Note on B24: user: Add to the following clause
Note on B29: user: Add to the following clause

## EARTHWORKS
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200D | SECTION C: EARTHWORKS
C.1 |  | EARTHWORKS STORMWATER CHANNELS AND BERMS
C.1.1 | 8.3.1.2 | Remove topsoil to nominal depth 150mm, stockpile and maintain
C.1.1.1 |  | (1) Gabion channels |  | m2 | 21000
C.1.2 |  | Bedding for gabions
C.1.2.1 | 8.3.4 (a) | Importing of G7 selected fill material as directed by Engineer |  | m3 | 4200
C.2 | SANS 1200DE | STORMWATER CHANNELS
C.2.1 | 8.3.3 | Excavation to line
C.2.2 | 8.3.3 a) | Material unsuitable for embankment. Excavate to line and level in all materials as if in soft or intermediate material. |  | m3 | 28000
C.2.3 | 8.3.3 a) and PSDB 8.3.2.1 a) | Material unsuitable for embankment and disposal of surplus material within 100m of the excavation utilising LIC methods. | LI | m3 | 7000
C.2.4 | PSDB 8.3.2.1 b) i) | Loading of surplus material utilising LIC methods for disposal by conventional methods including 10km free haul | LI | m3 | 1000
| PSDB 8.3.2.1 b) ii) | Loading and disposal of surplus material utilising conventional methods including 10km free haul |  | m3 | 6000
| PSDB 8.3.2.1 b) iii) | Detention pond shaping and rehapilitation |  | m2 | 21340
C.2.5 | PSDB 8.3.2.1 c) | Extra over PSDB 8.3.2.1 (a) and (b) for:
C.2.6 | PSDB 8.3.2.1 c) i) | soft excavation Class 2 | LI | m3 | 1500
C.2.7 | PSDB 8.3.2.1 c) ii) | intermediate excavation including prior ripping/loosing | LI | m3 | 750
C.2.8 | 8.3.3 b) | Material suitable for embankment from channel excavations |  | m3 | 11000
C.2.9 | 8.3.3 a) and PSDB 8.3.2.1 | Material suitable for embankment material and for embankment placing within 100m from the excavation utilising LIC construction methods and compaction by conventional methods | LI | m3 | 8000
SUB-TOTAL CARRIED FORWARD
brought forward
C.2.10 | 8.3.3 c) | Extra over for
C.2.10.1 | 8.3.3 b) (2) | Hard rock and boulder excavation B (PSD 3.1.2) |  | m3 | 2000
C.2.11 | 8.3.4 | Preparation of exposed surfaces
C.2.12 | 8.3.4 b) | Rip and re-compact insitu material for areas to be covered by berms and channels | LI | m2 | 10000
C.2.13 | PS DB 8.3.4 | Import and Place dump rock as instructed by Engineer |  | m3 | 500
C.2.14 | 8.3.5 | Forming of embankment
C.2.14.1 | 8.3.5 a) | Selected suitable material compacted in 150mm thick layers to 93% MOD AASHTO |  | m3 | 3150
C.2.14.2 | 8.3.5 a) | Selected suitable material from commercial sources, compacted in 150mm thick layers to 93% MOD AASHTO. (For backfilling behind gabion baskets - when instructed by the Engineer.) |  | m3 | 945
C.2.15 |  | Finishings
C.2.15.1 | 8.3.9 | Topsoiling
C.2.15.2 | 8.3.9 a) | Topsoiling | LI | m2 | 2100
C.2.15.3 | 8.3.9 b) | Seeding | LI | ha | 1
C.2.15.4 | 8.3.9 c) | Fertilizer | LI | ha | 1
C.2.15.5 | 8.3.9 d) | Watering | LI | ha | 1
C.3 | SANS 1200DM | EARTHWORKS (ROADS, SUBGRADE)-TEMPORARY DIVERSION
C.3.1 | 8.3.2 (a) | Preparation and stripping of Site/removal of topsoil to 150mm, stockpiling and maintaining |  | m3 | 10
C.3.2 | 8.3.3 | Treatment of road-bed
C.3.2.1 | 8.3.3 a) | Road-bed preparation and compaction of material to
C.3.2.2 | 8.3.3 a) 2) | Minimum of 93% of modified AASHTO maximum density |  | m3 | 10
SUB-TOTAL CARRIED FORWARD
brought forward
C.3.3 | 8.3.4 | Cut to fill |  | m3 | 10
C.3.3.1 | 8.3.4 a) | Compact to 90% of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 10
C.3.4 | 8.3.5 | Selected layer G8 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 10
C.3.5 | 8.3.5 | Selected layer G7 material compacted to 93 % of modified AASHTO maximum density (in layers of 150mm) |  | m3 | 10
C.3.6 | 8.3.7 | Cut to spoil
C.3.6.1 | 8.3.7 a) | In all materials other than hard excavation |  | m3 | 10
C.3.7 | 8.3.16 | G5 gravel surface layer compacted to 95% of modified AASHTO density (150mm) |  | m3 | 10
C.3.8 |  | Removal of temporay road
C.3.9 | 8.3.7 a) | Cut to spoil temporary road materials |  | m3 | 10
TOTAL CARRIED FORWARD TO SUMMARY

## Gabions
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200DK | SECTION D: GABIONS AND STONE PITCHING
D.1 |  | GABIONS AND PITCHING
D.1.1 | 8.2.1 | Surface preparation for bedding of gabions
D.1.1.1 | 8.2.1 a) | Cavities filled with approved excavated material or rock | LI | m2 | 9000
D.1.2 | 8.2.2 | Gabions
Galfan + PVC coated gabions with hexagonal woven wire mesh type 80(double twist wire mesh). The PVC Coating to sans 1580 is grey and has a nominal thickness of 0.5mm. Complete with partitions at 1m centres. Gabions to be filled with selected dump rock ( non weatherable, non-friable, well graded between 150mm and 250mm diameter, with specific gravity of 2.6, without asbestos seams) and tied into adjoining gabions.
D.1.2.1 | 8.2.2 a) | 2m x 1m x1m Galvan + PVC Gabion Unit Type-A | LI | m3 | 700
D.1.2.2 | 8.2.2 b) | 2m x1m x0.5m Galvan + PVC Gabion Unit Type-B | LI | m3 | 0 |  | Rate only
D.1.2.3 | 8.2.2 c) | 2m x 0.5 x 0.5m Galvan + PVC Gabion Unit Type-C | LI | m3 | 500
D.1.3 |  | Reno mattress
Reno mattress formed with a hot dipped galvanized 275mg/m2 coated with 4mm PVC coating (4mm SANS 1580) hexagonal double twist 3mm wire mesh type 60 with 0.08mm tolerance (SANS 675) filled with selected dump rock ( non weatherable, non-friable, well graded between 150mm and 250mm diameter, with specific gravity of 2.6, without asbestos seams) and tied into adjoining gabions.
D.1.3.1 | 8.2.2 | (a) 1000mm x 3000mm x 300mm | LI | m3 | 3600
D.1.3.2 | 8.2.2 | (b) 1500mm x 3000mm x 300mm | LI | m3 | 540
|  | (c) 1500mm x 6000mm x 300mm | LI | m3 | 900
D.1.4 | 8.2.3 | Extra-over 8.2.2 for packlng selected stone for exposed face | LI | m2 | 1 |  | Rate only
D.1.5 |  | Geotextile
D.1.5.1 | 8.2.4 | Mactex N20.2 (Non-woven geotextible manufactured with polyester continious filament fibres assebled by a needed punched treatment) | LI | m2 | 12000
SUB-TOTAL CARRIED FORWARD
brought forward
D.1.6 | 8.2.5 | Stone pitching | LI | m2 | 2000
D.1.7 | PSDK 8.2.8 | Erosion control blanket (SoilSaver® or Similar Approved) as instructed by the Engineer. | LI | m2 | 500
D.1.8 | PSDK 8.2.9 | (a) Y12 hot dipped galvanised ground anchor pegs 1.5m in length as instructed by the Engineer. | LI | No | 1000
TOTAL CARRIED FORWARD TO SUMMARY

## Stormwater Drainage
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | LIC | UNIT | QTY | RATE | AMOUNT
| SANS 1200LE | SECTION E: STORMWATER DRAINAGE
E.1 |  | STORMWATER DRAINAGE
E.1.1 | PSDB 8.3.2.1 | Excavation
E.1.2 |  | (c) Excavate, in all materials for portal and rectangular trenches (depth range and minimum width specified), backfill, compact and dispose of surplus material utilising Conventional Construction Methods | LI | m3 | 300
E.1.3 |  | d) Extra-over (E.1.1.1) for;
E.1.3.1 |  | i) Intermediate excavation including prior ripping/loosing | LI | m3 | 176
E.1.3.2 |  | iii) Backfill and compact by means of Labour Intensive Construction Methods in layers of 200 mm compacted to 90% MOD AASHTO | LI | m3 | 125
E.1.3.3 |  | iv) Disposal of surplus material by means of Labour Intensive Construction Methods within 100 m from the source of spoil material using wheel barrows | LI | m3 | 200
E.1.4 |  | (e) Excavate and dispose of unsuitable material from trench bottom utilising:
E.1.4.1 |  | i) Labour Intensive Construction Methods | LI | m3 | 20
E.1.4.2 |  | ii) Conventional Construction Methods |  | m3 | 20
CONCRETE CULVERTS
E.1.5 | 8.2.2 (b) | Supply and lay portal and rectangular culverts:
E.1.5.1 |  | (i) 2000mm (W) x 1500mm (H) x 75S |  | m | 50
E.1.5.2 |  | (ii) 1800mm (W) x 1500mm (H) x 75S |  | m | 43 |  | Rate only
E.1.6 | 8.2.9(a) | Brickwork for closing off existing rectangular culvert openings | LI | m2 | 30 |  | Rate only
SUB-TOTAL CARRIED FORWARD
brought forward
E.2 |  | CONCRETE AND STEEL WORKS FOR CULVERTS AND OPEN DRAINS
| SANS 1200GA | CONCRETE - SMALL WORKS
E.2.1 |  | Concrete:
E.2.1.1 | 8.1.3 | (i) Cast in situ conrete lining class 25/19 concrete: Type B concrete trapezoidal drain | LI | m3 | 50
E.2.1.2 | 8.1.4 | (ii) Class 30/19 for base slabs, headwall, wingwalls and apron slab complete with formwork, joints and class U2 surface | LI | m3 | 50
E.2.2 |  | Formwork:
E.2.3 | 8.2.1 | Rough
|  | i) Vertical formwork for F1 surface finish - Culverts | LI | m3 | 44
E.2.4 | 8.2.2 | Smooth
E.2.4.1 |  | i) Vertical formwork for F2 surface finish - Portal and Rectangular Culverts | LI | m2 | 34
E.2.4.2 |  | ii) Horizontal formwork for F2 surface finish - Portal and Rectangular Culverts | LI | m2 | 78.35
E.2.4.3 |  | iii) F2 surface finish to sides with formwater on the internal face only - Open drains | LI | m2 | 10
E.2.5 |  | Steel Bars
E.2.5.1 | 8.3.1 | (a) Mild steel bars: | LI | t | 2
|  | Galvanized mild steel D1 dowels: 16mm diameter,1200 long, covered with PVC sleeve and flexible end cap | LI | t | 2.4
E.2.5.2 | 8.3.1 | (b) High-tensile steel bars
|  | (i) Y20 steel bars | LI | t | 2
SUB-TOTAL CARRIED FORWARD
brought forward
|  | (ii) Y16 steel bars | LI | t | 0.5
|  | (iii) Y10 steel bars | LI | t | 0.2
|  | (iv) Y12 steel bars | LI | t | 1
E.2.6 | 8.3.2 | High-tensile welded mesh
E.2.6.1 |  | (i) Welded steel fabric (Ref 617) | LI | m2 | 141.95
E.2.6.2 |  | (ii) Welded steel fabric (Ref 311) | LI | m2 | 280
E.2.7 | 8.4.1 | Concrete backfill to rectangular culverts
E.2.7.1 |  | (i) Class 15/19 | LI | m3 | 19
E.2.8 | 8.4.2 | 50mm blinding Layer in class 15/19 Concrete | LI | m3 | 20
E.2.9 | 8.4.4 | Unformed surface finishes:
E.2.9.1 |  | a) Class U2 surface finish for Type B concrete side drain | LI | m2 | 67
E.2.10 | 8.5 | 10mm bitumen impregnated softboard:
E.2.10.1 |  | i) 5500mm x 165mm | LI | m | 25
E.2.10.2 |  | ii) 5500mm x 1025mm | LI | m | 40
E.2.10.3 |  | iii) 6100mm x 1800mm | LI | m | 15
E.2.10.4 |  | iv) 250mm x 250mm | LI | m | 10
TOTAL CARRIED FORWARD TO SUMMARY

## 8-STRUCTURED TRAINING
CONTRACT NO. : 017/MKLM/2025/2026 UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP MOSES KOTANE LOCAL MUNICIPALITY
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
B 8 |  | Provision of Structured Training
8.1 |  | Generic Skills | Prov.Sum | 1 | 140000 | 140000
8.2 |  | Entrepreneurial Skills | Prov.Sum | 1 | 140000 | 140000
8.3 |  | Training Venue | Prov.Sum | 1 | 20000 | 20000
8.4 |  | Handling Costs in respect of (8.1) to ( 8.3 ) above | % | 300000
TOTAL CARRIED FORWARD TO SUMMARY

## PHASE 3_SUMMARY
CONTRACT NO. : 017/MKLM/2025/2026 SCHEDULE OF QUANTITIES SUMMARY OF BILL OF QUANTITIES - UPGRADING OF 2.16KM STORMWATER IN GOEDEHOOP
Section | Description | Amount
R
1 | Preliminary and General
2 | Site clearance
3 | Earth Works
4 | Gabions
5 | Stormwater Drainage
6 | Provision of Structured Training
Subtotal 1
ADD | Contingency @ 10% (Solely for the use of the Client, and only on instruction to Contractor)
Subtotal 2
ADD | 15% VAT
TOTAL CARRIED TO FORM OF OFFER